## Project Parts
Twitter | Status | Program |  |  | Status | Database | Status | Web App |  |  | Status | Open Questions
Twitter API | Done | EC2/Docker | Python Container | streamer.py | To Start | RDS | To Start | Docker/Heroku | Python Container | Streamlit Web App | To Start
|  |  | Python Container | model.py | To Start
|  |  | Python Container | etl_job.py | To Start
|  |  | PostgreSQL Container | PostgresDB | To Start
|  |  | MongoDB Container | MongoDB | To Start

## Project Plan
[6 empty] | Set-Up | Program | Web App | Cloud | RNN | Wrap-Up | Present.
Task Name | Part | Duration (hr) | Complete by | Status |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Review Docker-compose | General | 0.5 | Day 1 | Done |  | 1 | 10.5 | 6 | 5 | 13 | 6 | 0
Review Heroku deployment | General | 0.5 | Day 1 | Done | Done | 1 | 10.5 | 0 | 0 | 0 | 0 | 0
Review Twitter Project | General | 1 | Day 2 | Done | Left | 0 | 0 | 6 | 5 | 13 | 6 | 0
Research Streamli functionality and design web app | Web App | 1.5 | Day 2 | Done
Design presentation | General | 0.5 | Day 2 | Done
Develop streamer.py & containerize | Program | 1.5 | Day 2 | Done
Develop model.py & containerize | Program | 1.5 | Day 2 | Done
Develop etl_job.py & containerize | Program | 1.5 | Day 2 | Done
Containerize MongoDB | Program | 1.5 | Day 2 | Done
Containerize PostgresDB | Program | 1.5 | Day 2 | Done
Add on conflict update sentiment score | Program | 0.5 | Day 3
Test everything up to sentiment model | Program | 2 | Day 3
Build web app | Web App | 1.5 | Day 3
Test web app using local connection | Web App | 2 | Day 3
Set up EC2 instance | Program | 2 | Day 4
Set up RDS instance | Database | 2 | Day 4
Import Docker architecture into EC2 | Program | 1 | Day 4
Review Deep Learning | Program | 4 | Day 5
Develop new python script model with RNN | Program | 4 | Day 5
Integrate model | Program | 1 | Day 5
Download past tweets to compare sentiment | Database | 4 | Day 5
Develop simple MLOpps (e.g. retrain model every new 100 data points) | Program | 2 | Day 6
Develop fail-safe for web app inputs | Web App | 2 | Day 6
Refactor code with pylint | Program | 2 | Day 6

## Web App
Requirements | Example | Notes
Input up to 4 company names | "Pfizer"
Input time to compute | 1 hour | Set maximum to avoid AWS costs
Output sentiment graph over time | Line chart with automatic labels | Graph which updates every 5 seconds
Output number of datapoints sentiment is based on | n = 1342 | For the first time a company is searched, take last 100 Tweets, return n = 100. As time goes on live streamer will collect
Return full dataset for particular company